## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | As a legal team member, I want to upload contract documents so the AI can analyze them | MUST HAVE | No Dependency | Ruchika Kengal | 3- Completed
S1 | S1 | US-001 | As a user, I want to see basic contract metadata extraction | MUST HAVE | Document Upload | Ruchika Kengal | 3- Completed
S1 | S1 | US-001 | As a compliance officer, I want to identify clause violations in contracts | MUST HAVE | identification | Ruchika Kengal | 3- Completed
S1 | S1 | US-001 | As a user, I want to view compliance risk scores | SHOULD HAVE | training ai model | Ruchika Kengal | 3- Completed
S1 | S1 | US-001 | As a user, I want to train the AI model with custom compliance rules | MUST HAVE | Basic Analysis | Ruchika Kengal | 3- Completed
S1 | S1 | US-001 | As a user, I want to generate compliance reports | MUST HAVE | Risk Analysis | Ruchika Kengal | 3- Completed
S1 | S1 | US-001 | As a user, I want to compare contracts against industry standards | SHOULD HAVE | Report Generation | Ruchika Kengal | 3- Completed
S1 | S1 | US-001 | As a user, I want real-time compliance monitoring | MUST HAVE | All Modules | Ruchika Kengal | 3- Completed
S1 | S1 | US-001 | As an admin, I want to manage user roles and permissions | SHOULD HAVE | System Setup | Ruchika Kengal | 3- Completed
S1 | S1 | US-001 | As a user, I want API integration with existing legal systems | COULD HAVE | Core Features | Ruchika Kengal | 3- Completed
Note on F1: ====== ID#AAABtt5Aa1Y Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 80 | 20 | 21 | 23 | 13 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Design document upload system architecture | 2025-09-10 | 2025-09-10 | Hariharan J | Design | 3- Completed | 3 | bar: Day 1 to Day 6
US-001 | 2 | Implement PDF/text document parser | 2025-09-10 | 2025-09-10 | Hariharan J | Coding | 3- Completed | 8 | Day 1: 1; Day 2: 2; Day 3: 2; Day 4: 1; Day 6: 2
US-001 | 3 | Develop metadata extraction module | 2025-09-11 | 2025-09-11 | Hariharan J | Coding | 3- Completed | 6 | Day 2: 3; Day 3: 3
US-001 | 4 | Create compliance rule database | 2025-09-11 | 2025-09-11 | Hariharan J | Database | 3- Completed | 6 | Day 2: 1; Day 3: 1; Day 4: 2; Day 6: 2
US-001 | 5 | Implement clause violation detection | 2025-09-11 | 2025-09-11 | Hariharan J | AI/ML | 3- Completed | 4 | Day 1: 2; Day 2: 2
US-001 | 6 | Design risk scoring algorithm | 2025-09-11 | 2025-09-11 | Hariharan J | Design | 3- Completed | 5 | Day 3: 2; Day 4: 2
US-001 | 7 | Build rule training interface | 2025-09-12 | 2025-09-12 | Hariharan J | Frontend | 3- Completed | 6 | Day 1: 8; Day 3: 2
US-001 | 8 | Implement ML model retraining pipeline | 2025-09-12 | 2025-09-12 | Hariharan J | AI/ML | 3- Completed | 4 | Day 3: 2; Day 4: 2
US-001 | 9 | Develop report generation engine | 2025-09-12 | 2025-09-12 | Hariharan J | Backend | 3- Completed | 8 | Day 1: 3; Day 2: 3; Day 3: 2
US-001 | `10 | Create report template designs | 2025-09-13 | 2025-09-13 | Hariharan J | Design | 3- Completed | 6 | Day 2: 2; Day 3: 2; Day 4: 2
US-001 | 11 | Integrate industry standard databases | 2025-09-13 | 2025-09-13 | Hariharan J | Integration | 3- Completed | 7 | Day 1: 2; Day 2: 2; Day 3: 3
US-001 | 12 | Build contract comparison module | 2025-11-01 | 2025-11-01 | Hariharan J | Coding | 3- Completed | 4 | Day 3: 2; Day 4: 2
US-001 | 13 | Design real-time monitoring system | 2025-11-01 | 2025-11-01 | Hariharan J | Design | 3- Completed | 4 | Day 2: 2; Day 3: 2
US-001 | 14 | Implement alerting mechanism | 2025-11-12 | 2025-11-12 | Hariharan J | Backend | 3- Completed | 6 | Day 2: 2; Day 3: 2; Day 4: 2
Note on D2: ====== ID#AAABtuEGXE4 Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABtt5Aa1E Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABtt5Aa1I Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABtt5Aa1M Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABtuEGXEw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABtuEGXFE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABtt5Aa1U Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABtuEGXFI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABtuEGXE0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABtuEGXE8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABtuEGXEs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABtt5Aa1Q Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABtuEGXEg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABtuEGXEo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABtuEGXFM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABtuEGXEk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABtuEGXFA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Document parsing accuracy issues with scanned PDFs | Implemented OCR preprocessing for scanned documents
Sprint 1 | Day 1 | Large file uploads causing timeout errors | Increased file size limits and added chunked uploads
Sprint 1 | Day 2 | Compliance rule conflicts in complex contracts | Created rule priority hierarchy system
Sprint 1 | Day 2 | Risk scoring algorithm giving inconsistent results | Calibrated scoring weights with legal expert input
Sprint 1 | Day 3 | ML model training taking too long with large datasets | Optimized training pipeline and added incremental learning
Sprint 1 | Day 4 | User interface for rule training too complex for non-tech users | Simplified UI with guided workflow
Sprint 1 | Day 4 | Report generation performance issues with multiple contracts | Implemented background job processing
Sprint 1 | Day 5 | Data visualization libraries compatibility problems | Researched and integrated alternative charting library

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2025-09-10 | 2025-09-10 | Hariharan J | Regular performance testing | Underestimating file processing complexity | Documenting architectural decisions | Implemented comprehensive file validation pipeline
2 | S1 | 2025-09-11 | 2025-09-11 | Hariharan J | Code review sessions | Skipping unit tests for tight deadlines | Daily standup participation | Established mandatory test coverage requirements
3 | S1 | 2025-09-12 | 2025-09-12 | Hariharan J | Legal domain expert consultations | Making assumptions about compliance rules |  | Scheduled weekly sessions with legal team
4 | S1 | 2025-09-13 | 2025-09-13 | Hariharan J | User feedback collection early | Complex configuration setups | Agile methodology adherence | Created user testing group from legal department
5 | S1 | 2025-11-01 | 2025-11-01 | Hariharan J | Cross-browser testing | Ignoring mobile responsiveness | Team collaboration | Added responsive design to all frontend components
6 | S1 | 2025-11-12 | 2025-11-12 | Hariharan J | Security audit integration | Hardcoding API endpoints | Continuous integration | Implemented environment-based configuration